## Sheet1
Milestone 6
Deadline
Front-End Complete |  |  | 2020-11-02
Progress Update |  |  | 2020-11-17
Back-End Complete |  |  | 2020-11-25
Testing/Debugging |  |  | 2020-12-01
Final Presentation |  |  | 2020-12-11
Description
Front-End Development |  |  | 2020-11-02
Making logo | Design logo for the website and add in the home page | Gyanendra | 2020-11-05
Pop-up window for details | Pop up window for products in the product pages | Trey | 2020-11-07
Footer | Footer for all the pages | Shristi | 2020-11-02
My Account Page (Orders before, change settings, logout) | Create a single page for all the users, where they can view their history of purchase, view and modify the personal information, and can logout/delete the account. | Shristi | 2020-11-02
My Cart Page | List out all the products user add in the cart, with more information like the card details, address, etc. | Trey | 2020-11-10
Linking everything together | Link all the pages together to make sure we can efficiently navigate our whole website | Everyone | 2020-11-20
Back-End Development |  |  | 2020-11-19
Search Button | Search the database for the product | Gyanendra | 2020-11-09
Functions |  | Gyanendra | 2020-11-19
Database | Store every single user detail on the database | Everyone | 2020-11-19
Categories
My Account |  | Shristi | 2020-11-20
Session | Start the session, store the user's details in sessions | Shristi, Gyanendra | 2020-11-02
Password (Encryption/Decryption) | Encryting the password using some php | Shristi | 2020-11-06
Forgot Password | Email the signup email to with the user's password, decrypt the password so that it is user readable. | Shristi | 2020-11-08
Orders | Fetch all the orders brought by the customers along with the current orders on progress | Shristi | 2020-11-15
Signout | Signout/Stop the session | Shristi | 2020-11-04
Shopping Cart |  | Trey | 2020-11-20
Cart(Total Price, Items) | Cart page will have products, have to calculate the total items and price of each products | Trey | 2020-11-12
Order Details | Go back to the details of each orders to view, change the products. | Trey | 2020-11-06
Payment page | Go to payment page from cart to enter the cardnumber to start the process. | Trey | 2020-11-18
Admin Area |  | Gyanendra | 2020-11-20
Admin Home | Homepage for admin(completely different form user's view), which has all the priviliges, can navigate through different navigation bar on side to modify the produvts, or the customers details. | Gyanendra | 2020-11-05
Total Products | Fetch all the products from the database, and count the total | Gyanendra | 2020-11-07
Edit Products | Fetch all the products from the database, and can change the details and even delete them from the database. | Gyanendra | 2020-11-09
Total Customers | Fetch all the customers from the database, and count the total | Gyanendra | 2020-11-10
Edit Customers | Fetch all the customers from the database, and can change the details and even delete them | Gyanendra | 2020-11-12
Total Men Products/Edit | Fetch all the products from the database filter by men, and count the total, modify the details, add more products, delete the product(if out of stock) | Gyanendra | 2020-11-15
Total Kids Products/Edit | Fetch all the products from the database filter by kids, and count the total, modify the details, add more products, delete the product(if out of stock) | Gyanendra | 2020-11-12
Total Women Products/Edit | Fetch all the products from the database filter by women, and count the total, modify the details, add more products, delete the product(if out of stock) | Gyanendra | 2020-11-10
View Payments |  | Gyanendra | 2020-11-15
View Orders | Fetch all the orders brought by the customers along with the current orders on progress | Gyanendra | 2020-11-14
Debugging/Testing | Debug our individual pages, and everyone meets virtually to see everything works as expected. | Everyone | 2020-11-27