## Sheet1
Milestone 6
Description |  | Deadline
Front-End Complete |  | 2020-11-02
Progress Update |  | 2020-11-17
Back-End Complete |  | 2020-11-25
Testing/Debugging |  | 2020-12-01
Final Presentation |  | 2020-12-11
Front-End Development |  | 2020-11-02
Making logo | Gyanendra | 2020-11-02
Pop-up window for details | Trey | 2020-11-02
Footer | Shristi | 2020-11-02
My Account Page (Orders before, change settings, logout) | Shristi | 2020-11-02
My Cart | Trey | 2020-11-02
Linking everything together | Everyone | 2020-11-02
Back-End Development |  | 2020-11-19
Search Button | Gyanendra | 2020-11-09
Functions | Gyanendra | 2020-11-19
Database | Everyone | 2020-11-19
Categories
My Account | Shristi | 2020-11-20
Session | Shristi, Gyanendra | 2020-11-20
Password (Encryption/Decryption) | Shristi | 2020-11-20
Forgot Password | Shristi | 2020-11-20
Orders | Shristi | 2020-11-20
Signup | Shristi | 2020-11-20
Shopping Cart | Trey | 2020-11-20
Total items/price | Trey | 2020-11-20
Order Details | Trey | 2020-11-20
Payment page | Trey | 2020-11-20
Admin Area | Gyanendra | 2020-11-20
Admin Login | Gyanendra | 2020-11-20
Total Products | Gyanendra | 2020-11-20
Edit Products | Gyanendra | 2020-11-20
Total Customers | Gyanendra | 2020-11-20
Edit Customers | Gyanendra | 2020-11-20
Total Men Products/Edit | Gyanendra | 2020-11-20
Total Kids Products/Edit | Gyanendra | 2020-11-20
Total Women Products/Edit | Gyanendra | 2020-11-20
Admin Logout | Gyanendra | 2020-11-20
View Payments | Gyanendra | 2020-11-20
View Orders | Gyanendra | 2020-11-20
Debugging/Testing | Everyone | 2020-11-27